## Slide 1: A Better Means of Identifying and Quantifying the Impacts of Shipbuilding Disruption
Originally presented at the 2013 Ship Production Symposium, Bellevue, WA, November 2013. Posted with the permission of the Society of Naval Architects and Marine Engineers (SNAME). Material originally appearing in SNAME publications cannot be reprinted without written permission from the Society, 601 Pavonia Ave., Jersey City, NJ 07306.

## Slide 2: Contents
The Problem
The Cause
The Result
Types of Impacts
Responding to the Impacts
Disruption Analyses
Having the Data
Agreeing on the Answer
Summary

## Slide 3: The Problem

## Slide 4: Building a ship to order is often a less-than-perfect experience
Owner’s specification might be flawed
There may be problems with ship design, construction, and outfit
Suppliers may be late, or their prices might increase since the bid
Owner may not provide timely review, inspection, and approval
The weather may not cooperate

## Slide 5: Once a problem is recognized, parties want to assess the impacts
Seeks to scope the problem, identify the causal event, and measure the impact in terms of cost and delay
Seeks to validate the existence of the problem and the cause, and check whether the additional cost and time are being properly assessed
If affected, is assessing the situation in ways similar to the owner
Builder
Owner
Insurer

## Slide 6: Assessment can be difficult
By the time a problem is recognized, the cause may have passed and it is too late to collect relevant data
Absent data linking cost or schedule changes to the suspected event, it is difficult to isolate those impacts from other program issues

## Slide 7: The Cause

## Slide 8: It is not difficult to imagine examples of disruptive events
Builder-Caused
  An infrastructure upgrade in the yard falls behind schedule and impacts production
Owner-Caused
  Plan review falls behind schedule or inspectors are unavailable, so the yard needs to proceed without approval or let the schedule slip
Supplier-Caused
  Major equipment is delivered late
Environment-Caused
  A storm causes damage that interrupts production

## Slide 9: Nor is it difficult to imagine how the needed data would be unavailable
Builder
  Does not expect a well-planned infrastructure upgrade to create problems and so is unprepared to tracks its impacts
  If supplier is late, the cause and impact will be clear, so it is not necessary to track the effects
Owner
  Staffs the project with the expectation of keeping up with design and production and so does not expect to create problems
Both
  We can weather the storm, so we need not track the effects
  Whatever happens, it cannot be our responsibility

## Slide 10: The Result

## Slide 11: Seemingly simple events can produce complicated outcomes
The event causes multiple impacts that accumulate and affect many aspects of the project and other yard programs
As builder and owner take steps to reduce the impacts, they may create additional problems
  This creates additional causes and effects that need to be analyzed

## Slide 12: It is a complex set of events with often conflicting views
Owner’s Data
Builder’s Data
Owner’s Analysis
Owner’s Version of the Truth
Disruptive Event
Clash
Builder’s Remedial Action
Builder’s Analysis
Builder’s Version of the Truth

## Slide 13: Without the data, all parties resort to estimating and finger pointing
The shipyard often has the most complete data that is used to manage the project
The owner uses its own data and what shipyard data it can access
Each party is likely to take a stance that minimizes its responsibility and cost

## Slide 14: Complexity of impacts can create confusion and disagreement
What actually happened?
Who was at fault?
How much did it cost?
Whose analysis is correct?
What impact did it have on other aspects of the project or on other programs in the yard?
How, if at all, was disruption addressed in the ship construction contract?

## Slide 15: By the time the parties begin on a solution, animosity has surfaced
The approach to answering the questions becomes antagonistic rather than cooperative
Both sides may seek legal counsel
Whatever the outcome, it is still the result of some guesswork and well-intentioned but probably faulty estimates

## Slide 16: Types of Impacts

## Slide 17: It may be helpful to break down complex impacts into categories
Elements of a project typically impacted:
  Labor
  Less Experienced Work Teams
  Decrease in Productivity
  Manpower Reassignment
  Overtime to Maintain Schedule
  Increase in Level-of-Effort Work
  Additional Support Labor
  Out-of-Sequence Work
  Increased Use of Subcontract Labor
  Increased Supervision
  Increased Quality Assurance
  Increased Engineering and Logistics
  Infrastructure
  Shop or Worksite Disruption
  Facility or Equipment Unavailability
  Material
  Unavailable or Damaged
  Cumulative Disruption

## Slide 18: Category measurement may have common and unique challenges
Impact Category | Challenges
Less Experienced Work Teams. Additional man-hours due to unplanned mix of employee skills, seniorities following the event | The shipyard may not have defined the optimal mix Supervisors may not record reassignment of personnel Additional man-hours are not tracked relative to the event
Decrease in Productivity. Increased man-hours due to changes to less efficient processes and methods caused by event | Switch to less efficient process may not be recorded Additional man-hours are not tracked relative to the event
Manpower Reassignment. Additional man-hours resulting from moving manpower from areas of expertise to other areas due to the event | Supervisors may not record reassignment of personnel Additional man-hours are not tracked relative to the event

## Slide 19: Category measurement may have common and unique challenges
Impact Category | Challenges
Overtime to Maintain Schedule. Additional man-hours expended in OT or additional shifts in an effort to make up lost time resulting from the event | The reason for additional hours may not be recorded Overtime or additional shifts may fail to get the program back on schedule and so may not benefit the owner
Shop or Worksite Disruption. Additional man-hours resulting from shops or work areas being completely/partially out of service following the event | System fails to capture additional man-hours associated with work-arounds
Increase in Level-of-Effort Work. Schedule slippage drives additional LOE hours for employees supporting vessel construction labor | System fails to identify the additional days resulting from the event, so additional LOE man-hours cannot be isolated
Facility or Equipment Unavailability. Extra man-hours caused by waiting due to yard services/facilities being unavailable following the event | System fails to capture additional man-hours spent waiting for cranes or other support

## Slide 20: Category measurement may have common and unique challenges
Impact Category | Challenges
Material. Extra man-hours due to material damage, lateness, etc. | System fails to capture additional man-hours spent waiting for material to arrive or to be repaired or replaced
Out-of-Sequence Work. Additional man-hours resulting from event-caused changes in processes and suboptimal working sequences | System fails to capture when process or work sequence changed, so additional man-hours cannot be linked to event
Additional Support Labor. Additional man-hours (over/above LOE personnel) required to support event-caused construction labor/process modifications; may include planning, engineering, material control, service department employees | System fails to capture additional work duration associated with event so additional man-hours cannot be linked to event-caused delay
Increased Use of Subcontract Labor. Additional personnel required to offset other impacts and productivity issues | Shipyard may regularly use subcontract labor, and system fails to link additional use to the event

## Slide 21: Category measurement may have common and unique challenges
Impact Category | Challenges
Increased Supervision. Additional supervisory man-hours to complement increased direct vessel hours | System fails to identify additional man-hours resulting from event, so event-caused additional supervisory hours cannot be isolated
Increased Quality Assurance. Additional man-hours to ensure quality standards when following alternate plans due to event | System fails to identify changed work resulting from event, so event-caused additional QA hours cannot be isolated
Increased Engineering and Logistics. Additional engineering and logistics man-hours to support extra labor costs associated with the other factors | System fails to identify additional man-hours resulting from event, so event-caused additional engineering and logistics hours cannot be isolated
Cumulative Disruption. The sum of all factor impacts drives an additional compounding of lost labor hours | Given all of the uncertainty listed above, quantification of cumulative disruption is not likely to be accurate

## Slide 22: Responding to the Impacts

## Slide 23: The challenges can be addressed through analysis
Analysis steps include:
  Defining the framework of the analysis
  Capturing relevant data
  Determining schedule delay
  Quantifying the increased costs
Although, without the best data, the analyses may be imperfect

## Slide 24: Disruption Analyses

## Slide 25: Several quantification methods are available
Project Based Model
  Requires a comparable undisrupted period
  Shipbuilding rarely exhibits a steady state
Total Cost Accounting
  Modified total cost method attempts to isolate shipbuilder- and owner-responsible costs
  Top down methods fail to designate responsibility for unknowns
Industry Standard Approach
  Allows a bottom up analysis
  Estimates missing facts by applying best practice standards

## Slide 26: Cumulative disruption must be added to direct impacts
Cumulative impacts occur when multiple changes disrupt unchanged work in the same vicinity
The calculation is based on a percentage ratio of impacted hours (changed) to baseline hours (unchanged)

## Slide 27: Having the Data

## Slide 28: What data are needed?
Understanding the analyses required to assign and quantify the impacts enables the required data to be identified
The requirements are fairly consistent, regardless of the event being analyzed

## Slide 29: Certain data are critical to delay and disruption analyses
Category | Supporting Data | Disruption Critical | Delay Critical | Data Volume
Schedule | Key Event Schedules |  | X | Low
 | Critical Path Schedules |  | X | Low
 | Planned Durations and Sequencing |  | X | Low
 | Master Schedule and Changes |  | X | High
 | Pre-Erection and Erection Schedules |  | X | High
 | Material In-Yard Schedules |  |  | High
 | Contract Modifications and Advances/Delays |  |  | Medium
 | Test Schedule, Plans, and Trial Sequencing |  |  | Medium
 | Detailed Schedules by Shop, Process Lane, or Area |  |  | Medium
 | Compartment Schedules |  |  | Medium

## Slide 30: Certain data are critical to delay and disruption analyses
Category | Supporting Data | Disruption Critical | Delay Critical | Data Volume
Manpower | Manning Supply/Demand Forecast and History |  | X | Medium
 | Level of Effort Hours Summary by Departments/Tasks |  | X | Medium
 | Direct Labor, Overtime, and Rework by Work Breakdown Structure | X |  | Medium
Performance | Cost/Schedule Performance Reports | X | X | Medium
 | Earned Value Database (EVMS in Gov’t Contracts) |  |  | High
 | Program and Business Management Reports |  |  | Medium
 | Work Package/Bill Database | X |  | High

## Slide 31: Certain data are critical to delay and disruption analyses
Category | Supporting Data | Disruption Critical | Delay Critical | Data Volume
Shipbuilding Facilities | Shop Demand and Capacity Including Shutdowns | X | X | Low
 | Outsourcing Statements of Work |  |  | Medium
 | Facilities and Capital Equipment Upgrades |  |  | Low
Accounting | Historical Returned Cost Data | X |  | Medium
 | Annual Operating Budget, Allocations, and Changes |  |  | Medium
 | Sales and Margins Financial Database |  |  | High
 | Customer/Supplier Requests for Equitable Adjustment |  |  | Low

## Slide 32: Failing to collect data as events occur creates problems
A causal link between the loss and the event is required
  However, capturing the disruptive event data in a discrete account – assignable to a specific cause – is generally not done
Thus, cause and effect cannot be linked
  This leads to disagreements as the builder, owner, and insurer must rely instead on guesswork and estimates, often developed independently

## Slide 33: Data collection must be proactive rather than reactive
Why wait for a disruptive event and then try to reconstruct the impact, wishing you had real time data?
Shipbuilders and owners can build this data collection into the program
  May take some time and cost to accomplish
  Downstream benefits make it worthwhile
    It will make the quantification of impacts and settlement of cost overruns and delays more amicable and less costly

## Slide 34: A data framework must be designed
For a disruptive event, it will be necessary to identify:
Event
Start and end date
Beginning and end of impact
Location of disruption
Work packages affected
Man-hours expended due to the event
  Not in baseline work or caused by other events or inefficiencies
Increase in work duration resulting from the event
  Not caused by other events or inefficiencies
Decisions and/or procedures affecting delay or expenditure of man-hours
  Reassignment of personnel or re-sequencing of work
  Note that these decisions and procedures have impacts of their own that need to be captured
Once a shipyard establishes the means of collecting these data, the framework will be reusable with minor modifications for each contract.

## Slide 35: A data collection approach is required
Capturing the data will require training and incentives
  For supervisory personnel and workers to think differently about measuring and tracking work
When work is not being executed as planned – as identified in the master schedule or as described in the work package or bill – the workers and their supervisors need to identify why it is different

## Slide 36: The solution will not be easy
This analysis of change on a daily basis will require some time and thought
It is likely to be somewhat disruptive until it becomes part of the everyday routine
In order to support cooperative analysis, owners must be involved
  Review the supervisors’ and workers’ reports on a regular basis

## Slide 37: The new approach will improve the level of collaboration
Builder’s and
Owner’s
Data
Joint Analysis
Single Version of the Truth
Builder’s Remedial Action
Disruptive Event
Agreement

## Slide 38: An objective third party team can help with design and agreements
How do shipyards and owners initiate this change?
  First identify the needed data
  Determine how it will be collected, retained, shared, and used
  A third party may be best suited to work with both parties to enable the process
    Help the parties to agree on the approach, develop the data structure, and use the data to calculate delay and disruption and support each claim element with documented causal links

## Slide 39: Agreeing on the Answer

## Slide 40: Using agreed-upon data should yield fewer owner-builder disputes
Both parties will know what specific questions to ask and where to find the answers when seeking data
  It will not require wading through vast information repositories
This will ultimately improve the promptness and accuracy of a settlement

## Slide 41: Summary

## Slide 42: Summary
A better way to address shipbuilding disruption is needed
Data collection, claim methodology, and the settlement approach should be a joint effort
Parties should not hinder the very start of the process by questioning the validity of the data

## Slide 43: Summary
A strategic framework for data collection and analysis can bring order to otherwise confusing proceedings
Independent experts can assist with:
  Structuring the new data identification and gathering framework
  Data collection and discovery
  Assessment methodologies